## Academic Innovation
Proposed Phase 2 Roll-Out
Strategy #1: Academic Innovation: Advance an engaging holistic teaching and learning environment resulting in a seamless student experience that prepares them to embrace life’s opportunities.
Objective 1: Create pathways from non-credit offerings to credit programs.
1 | Create a task force to evaluate Bristol's current approach to awarding Credit for Prior Learning and develop recommendations for improvements, as needed. | V. Rege | Spring 2021 | Need internal marketing - work with co-chairs of the taskforce | X
| Meet with CPL Team to discuss the names that could be a part of the task force | Sandy, Barbara, Vinnie | DONE
| Develop the scope of work for the task force | Sandy, Barbara, Vinnie | DONE
| Finalize the names of the task force members | Sandy, Barbara, Vinnie | DONE
| Create quarterly meeting schedule and send invites | Barbara | DONE
| Hold the kick off meeting | Sandy, Barbara, Vinnie, Taskforce members | DONE
| Create Team folders to store task force meeting notes and other related documents | Barbara | DONE
2 | Work with industry and community partners to identify opportunities for awarding Credit for Prior Learning as a gateway to credit programs. | V. Rege | Spring 2021 |  | X
| Create a repository of the current CPL industry and community partners | Sandy Lygren, Barbara Cadima | Done
| Work with Business Solutions to create a plan to identify industry and community partners | Vinnie Rege, Sandy Lygren, Business Solutions | Ongoing
| Create a communication plan to deliver the advantages of CPL to potential industry partners | Vinnie Rege, Sandy Lygren, Barbara Cadima | Ongoing
| Connect with at least 3 solid leads for awarding CPL as a gateway to credit programs | Vinnie Rege, Sandy Lygren, Business Solutions | Ongoing
3 | Develop and distribute surveys for faculty and students regarding their preferences for and satisfaction with online education at Bristol, resulting in a set of actions to improve online learning. | A. Medeiros (JP) | Spring 2021 | new survey to adjuncts about modality preference being done in Feb. | X
| Obtain best practices in online learning for Bristol from online learning task force. ( 3 people from union 3 administrators) - Chad chair | Collaborate with Mike Murphy and online learning task force. | Spring 2021 | rubric for online learning done
| Review online learning task force recommendations to enhance the quality of online learning at Bristol. | Collaborate with Mike Murphy and online learning task force. | Spring 2021 | We are currently making orientation mandatory and re-branding the e-learning 101 training
| Develop student and faculty surveys addressing online teaching and learning based on task force recommendations. | Collaborate with Data and Technology Council. | Spring 2021
| Launch surveys and strive for a 50% response rate or higher. | Promote surveys with Marketing and Communications. | Fall 2021 | Survey as requested by the union
| Analyze results from online teaching and learning surveys. | SAIR staff will analyze results. | Spring 2022
| Disseminate results through Bristol Weekly, PLT, ALT, SSEM, accessBCC, professional development opportunities, etc. | Collaborate with employees throughout the college to discuss and apply results. | Spring 2022
| Establish recommendations for improvement based on survey results and provide to online learning task force. | Collaborate with Data and Technology Council. | Spring 2022
3 | Provide ongoing professional development to faculty teaching online, with an emphasis on equity-minded pedagogy | W. Duffy | Fall 2021 | Required 4 trainings - blackboard (2), equity training, universal design | X
| Collect existing online trainings into a single catalog, and collate by topic | Histories from CITE Lab, IT, and HR trainings from the past | Fall 2020 | 172 trained in January - total trained between 500-600
| Design and Complete "Train the Trainer" program on Equity in Online Training | Money for Liza Talusan course or alternate, (compensated) trainers | Done
2 | Develop a plan for collecting and analyzing student success data from courses including HIPs. | J. Puniello | Fall 2021 |  | X
| Once institutional HIPs are identified, determine appropriate variables for data collection | Deans, Dep't Chairs, subject matter experts, CTL, Jen Dekkers | 2021-05-21 | Top 5 HIP's for Bristol identified and will be incorporated into the pilot programs in the Fall by the academic area deans
| Collaborate with ITS to create an Argos report for HIPs data collection | ITS | 2021-05-21 | Fall 2021 all courses will be coded and data will be collected
Report benchmark data to stakeholders
4 | Require internships for career programs. | V. Rege | 2020-2024 |  | X
| Generate a list of career programs across the college and identify which of those have Internship requirement | Jenn Erilus, Pam Fournier, Vinnie Rege | DONE
| Create a communication plan to assist Deans, chairs and faculty in those programs to make decisions pertaining to inclusion of internship course | Jenn Erilus, Pam Fournier, Vinnie Rege | Ongoing
| Work with department stakeholders to develop an internship course as a part of their curriculum | Jenn Erilus, Pam Fournier, Vinnie Rege | Ongoing
| Incorporate Internship requirements in at least 3 additional career programs that do not have internship requirement | Jenn Erilus, Pam Fournier, Vinnie Rege | Ongoing

## Equity and Student Success
Proposed Phase 2 Roll-Out
Strategy #2: Equity and Student Success: Share responsibility for the success of our students and employees by improving equity-mindedness and ensuring institutional support that closes equity gaps.
Objective 2: Recruit, retain and develop a diverse community of employees.
3 | Provide training on unconscious bias, racism, equity, and inclusion to all interview committees. | Gia Sanchez (GC) | Spring 2021
| Infuse AA Officer into recruitment/Search Committee Process to ensure equitable consideration of qualified candidates. Corresponds with Equity & Student Success, Objective 2, Action 4 where Laura Carreiro is the lead. | Process Improvement Specialist | Pending
| Provide Search Committee training to equity representatives serving on search committees to ensure equitable recruitment practices are followed. Corresponds with Equity & Student Success, Objective 2, Action 4 where Laura Carreiro is the lead.uniformly.Corresponds with Equity & Student Success, Objective 2, Action 4 where Laura Carreiro is the lead. | Process Improvement Specialist | By the end of Spring 2021 | Look at Lane University equity - define what the core competencies what we want our employees to have
4 | Re-evaluate employee recruitment practices to ensure the intentional recruitment of diverse candidates. | L.Carreiro (GC) | Spring 2021
Objective 3: Increase the student conversion rates, from outreach to enrolled, with specific intention to under-represented groups.
2 | Develop and implement a process and cycle for regularly reviewing and analyzing student data to identify and address equity gaps in access. | A. Medeiros (JP) | Spring 2021
| Identify key metrics and under-represented populations and define in data dictionary. | Collaborate with Data Governance Team and PLT. | Spring 2021
| Conceptualize ways to systematically review and analyze data with an equity lens. | Collaborate with Data Governance Team and PLT. | Spring 2021
5 | Conduct focus groups with students to understand barriers to enrollment before and during the registration and onboarding process, identifying actions to address challenges for students, particularly minoritized students. | Emma Montague | Spring 2021
| Set up Focus Group for all 2020 Fall Admits who successfully completed New Student Orientation to understand their experience. | Invite member of the Equity Council to join focus groups and offer input on questions for attendees. | Spring 2021
| Set up 2nd Focus Group/ or survey for students who applied for Bristol but did not register for classes to understand potential barriers. | Admissions.
6 | Create a process for regularly evaluating pedagogical practices and materials through an equity lens. | Julie Jodoin/ RD Confirmed | Spring 2021
| Gather current E&I evidence-based initiatives and their assessments to train Equity and Inclusion Council members on key elements of inclusive feedback for sustainable and consistent involvement. Establish this E&I Council insight as a core element of shared governance for all college decisions. E&I must become part of our college culture. | E & I Council Steering Committee; CGC | 2021-03-21
| Gather qualitative data and recommendations from student focus groups, run each semester with minoritized groups across all campuses, including ABE and Workforce Development, addressing consistent questions. Institutionalize a response from student focus group data each semester across all entities of the college. | E&I Council Student Subcommittee/Diversity Officer/Student Services Council/Learning Council/Academic Affairs | 2020-05-21 | Higher education innovation fund - equity audit - funding begins in April - Lead instiution is Holyoke community college
| Institute an inclusive student-centered syllabus review with a clear, concrete rubric that promotes student perspective and inclusive pedagogy. | MCCC/Academic Affairs/LCTL/TLSD partners http://cue-equitytools.usc.edu/ | 2020-05-21
| Establish an Accessibility Checklist with guides/tipsheets for all college constituents to understand and use routinely for web-based material, handouts, and resources. Enforce compliance with accessibility checklist - including web-based media being captioned accurately in all course spaces, regardless of student enrollment disability status. | Marketing/ITS/ODS/CITE/Operations Council/CGC/MCCC/Academic Affairs/Fac Prof Staff Senate | 2020-05-21
| Review materials used from all SSEM entities from an Equity and Inclusion lens for both inclusive pedagogy and accessibility. | SSEM VPLT/Student Services Council/ITS/ODS/E & I Council Institution Subcommittee | 2020-05-21
| Institutionalize process for identifying which materials are translated into which languages on our website and in various departments. | ITS/Marketing & Communications/ESL/SSEM VPLT | 2020-01-21
| Institute and incentivize professional learning communities focused on inclusive pedagogy. | Academic Affairs/Human Resources/LCTL/MCCC/Fac Prof Staff Senate | 2020-05-21 | more explanation? - faculty institute about inclusive peadagogy - Jen P.

## Organizational Excellence
Proposed Phase 2 Roll-Out
Strategy #3: Organizational Excellence: Create a culture of innovation through improved processes and collaboration, modern technology and ongoing professional development to support student and employee success.
Objective 1 : Align the existing culture of the organization with our core values.
4 | Create an employee recognition program that highlights exceptional demonstrations of the institutional values. | Laura Carreiro | Spring 2021
| Determine what type of recognition would have meaning to people | Either a Council/Senate or perhaps a survey to the entire college to see what people want? | DONE
| Using feedback from employees, create specific programs/awards that highlights work that ties in with institutional values | Staff Senate/Faculty & Professional Staff Senate | Spring 2021 or later
| Review list of available awards in the community that Bristol employees could be nominated for; select awards to promote in concert with PLT and Operations Council | Human Resources | Ongoing
Objective 2 : Increase digital literacy among all Bristol students.
6 | Incorporate LMS training into orientation for students and faculty. | Will Duffy | Spring 2022
| Build an Asynchronous Learning Management System training guide module for faculty (guide for professors) | Assistance and Leadership from Cite Lab | Spring 2021
| Create/develop a Faculty Specific Orientation and/or Faculty Handbook that LMS info can be integrated into | HR, Deans, info on current orientation as it is now | Spring 2021
| Integrate Asynchronous LMS training modules for faculty into new Orientation | Assistance from CITE Lab, Deans | Done
Objective 3: Increase efficiency and equity-mindedness through process improvements across the College.
1 | Identify methodology and schedule for conducting business process reviews, ensuring review is completed through an equity lens. | Kathy Martin | Spring 2021
| Identify the highest risk areas which would benefit from a business process review | PLT / Risk Committee members | 2021-04-30
| Out of the inventory of the highest risk areas, identify three business processes to perform business process review | PLT / Risk Committee members | 2021-04-30
| Document methodology to be used to define process; e.g. flowcharts, business narratives, etc. Define desired deliverable. | K.Martin | 2021-04-30
| Agree on the scope of each business process review; include beginning and end points and the time frame needed to perform the review (the scope will influence the amount of time required) | VP responsible for area under review, other Department resources depending on the area under review | 2021-05-30